## Week-1
Daily Stand-up Meeting Report
Week: Jun 12 - Jun 16
Project Name: Slack/Hipchat collaboration tool
Team Name: Phoenix
| Monday | Tuesday | Wednesday | Thursday | Friday
Sanjay Bedudoori | 1) First day of project | 1) Explored slack tool | 1)Roles and responsibilities known | 1) partially completed problem statement | 1) Learned pull,push, commit in github
| 2) Explore Slack/Hipchat tools | 2) Deciding on roles & Respnisbilities | 2) writing problem statement | 2) Exploring github | 2) Gathering requirements of project
| 3) No obstacles | 3) pending exploring on other collaboration tool | 3) No obstacles till now | 3) No obstacles till now | 3) Have to learn more on merge conflict
Venkata Bhardwaj Avasarala | 1) Assigned with project groups and project | 1) Discussed the functionalities of slack and hipchat | 1) Decided the roles and assigned to take care of the assigned roles. | 1) Researched on different collaborative tools and discussed about it with the team | 1) Had a brief discussion on the different tools available and discussed the SWOT of them.
| 2) Need to check different functionalities of Slack and Hipchat collaborative tool. | 2) Need to decide the roles and features to be included in the project | 2) Need to focus and research more on collaborative tools | 2)Discuss on what to include in the project and the possible platforms for it | 2)Need to discuss with client more specificly to get a clear idea what he is expecting?
| 3) No issues faced | 3)No issues faced | 3)No issues faced | 3)No issues faced | 3)No issues faced
Sudharshan Reddy Kankara | 1) Project groups were assigned | 1) Got a brief idea on collaboration tools | 1) Roles for individual team members are assigned | 1)Researched more about collaboration tools | 1) Got some ideas on features to implement in our project
| 2) Research on collaboration tools | 2) Need to decide on the roles of individual team members | 2) Need to research more about different collaboration tools | 2) Need to find out different features that we can implement in our project | 2) Need to do more research on features to implement in our project
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Shravani Alampalli | 1) Project groups were assigned | 1) Assigned roles and researched on my role | 1) Researched on the requirements of client | 1) Research on the implementation techniques | 1) Done with some research on project
| 2) Research on hipchat | 2) Research on existing system | 2) Researched on existing system about the requirements given by client | 2) Reading the implementation techniques | 2) Should write down some key constraints of the project.
| 3) No issues till now | 3) No issues till now | 3) Need to know more about requirements | 3) No obstacles | 3) No issues
Hemanth Sai Kishore Nersu | 1) We are assigned groups | 1) we as a team assigned roles | 1) Researched some collaboration tools | 1) Done some researching about the requirements | 1) Read about the reqirements
| 2) went through some collabration tools | 2) Got to known about the project | 2) Discussed some tools with client | 2) Going through the existing system | 2) Should meet client for clear understanding of requirements
| 3) No major issues till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No major issues till now
Anudeep Reddy Mallidi | 1)Got to know the project and roles | 1) Analyzed the requirements of project | 1)Done some research on existing tools like slack | 1)Got a very breif idea about collaboration tools | 1) Noted few key requirements from the client meeting
| 2) yet to decide roles | 2) Understand more on project requirements | 2) Read through the drawbacks of existing system | 2) Learn about what collaboration features are most important | 2) discuss with team about project requirements
| 3)No obstacles till now | 3)No major issues till now | 3)Should have a clear view about the requirements | 3)No obstacles till now | 3)No obstacles till now
Vineeth Gajula | 1) Project groups were assigned | 1) Studied few existing tools like slack and hipchat | 1) Known about project roles | 1) Learned more about the project requirements | 1) Got breif idea about the project requirements
| 2) Research on collaboration tools | 2) Learn about the project requirements | 2) Take some notes about requirements | 2) Meeting with client to know the project features | 2) Meet with team to discuss about project
| 3) No obstacles till now | 3) No issues till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week-2
Daily Stand-up Meeting Report
Week: Jun 19 - Jun 23
Project Name: Slack/Hipchat collaboration tool
Team Name: Phoenix
| Monday | Tuesday | Wednesday | Thursday | Friday
Sanjay Bedudoori | 1) Gathered requirements of project | 1) Explored API for Git Hub | 1) Decision on addition on "task managemen" requirement to project | 1) Designing case diagrams for "task management" requirement | 1) Case diagram for task managment completed
| 2) API for github to integrate | 2) Database decision, whether SQL or NO SQL | 2) Case diagrams for task management requirement | 2) Behind the schedule, as case diagrams are not drawn yet | 2) Will start documenting requirement document for "Task management" requirement
| 3) No Obstacles | 3) More to explore on Git Hub API | 3) No obstacles | 3) Issue with what privileges can be given to users | 3) Pending proof reading of use cases by others
Venkata Bhardwaj Avasarala | 1) Had a dicussion with client and clarified some requirements more specifically and discussed with team more elaborately | 1) Discussed different features explored with the team | 1) Key Requirements were finalized | 1) Tested Google Drive API by integrating in different platforms C#, Web application, Windows standalone application. | 1) Prepared Use case for google drive integration
| 2)Explore different features like screensharing encrypting messages etc. | 2) Create a test project and check the usage of Google Drive API's feasibility | 2) Need to work on Gogle Drive Integration Use Cases | 2) Need to prepare use cases for Google Drive integration with our collaboration tool. | 2) Preparing test cases for Google Drive integration and chat tool
| 3) No issues faced | 3)No issues faced | 3) No Major issues faced | 3) Problems faced while integrating with standalone application in windows as proper documentation was not available in the google website. | 3) No major issues faced.
Sudharshan Reddy Kankara | 1) Decided on features to implement in our project | 1) Did some research on requirements | 1) Did some reasearch on chatting tool | 1) Did further research about chatting application | 1) Created use case for chatting application
| 2) Need to do reasearch on requirements | 2) Need to do further research on requirements | 2) Need to do further research on chatting application | 2) Need to work on use cases | 2) Need to work on requirements document for chat tool
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Shravani Alampalli | 1) Got idea about client requirements | 1) Gone through the requirements document | 1)After some research finalised key functional requirements | 1) Did work on task assigning | 1) Preparing presentation for mid-term presentation
| 2) Should go through the client requirements | 2) Should do some research on the requirements that whether we can implement or not and issues facing while implementing | 2) Need to work on task assigning | 2) Need to work on mid-term presentation | 2) Preparing test cases for task assigning
| 3) No obstacles | 3) No issues | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Hemanth Sai Kishore Nersu | 1) Had meeting with client | 1) Got clear understanding of requirements with client | 1) Finalized some key requirements | 1) Design the use cases of the shared document | 1) Prepared Test cases and did proof reading for moqups
| 2) Got to more about the details of the project | 2) went through the client requrements | 2) Need to work on use cases | 2) Need to work for test cases and prototypes | 2) Need to work on mid tem presentaion
| 3) No obstacles | 3) No issues | 3) No obstacles | 3) No issues | 3) No issues
Anudeep Reddy Mallidi | 1) Created some hipchat accounts to know the existing system | 1) Research on implementation of existing system | 1) Got detailed information about requirements | 1)finished designing moqups and handed over to the team for corrections | 1) Finished final corrections for the moqups
| 2) Research on existing system | 2) Comparing requirements with existing system | 2) Need to research on moqups for the project | 2) Need to work on test cases for shared calender requirement with vineeth | 2) Need to work on mid term presentation
| 3) No obstacles | 3) No issues | 3) No issues | 3) No issues | 3) No issues
Vineeth Gajula | 1) Discussed project requirements in the Team meeting | 1) Known the project requirements from the client | 1) Known key functional requirements from the client | 1) Finished writing the functional requirement 1 for shared calendar | 1) Drawn a use case diagram for shared calendar
| 2) Meet with client to get know more about project requirments | 2) Note key functionalities about project with client | 2) Document the functional requirement for Shared Calendar | 2) Draw use case diagram for shared calendar | 2) Develop test case for the functional requirement for calendar
| 3) No obstacles | 3) No issues | 3) No issues | 3) No Issues | 3) Test plan needs more depth
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week-3
Daily Stand-up Meeting Report
Week: Jun 26 - Jun 27
Project Name: Slack/Hipchat collaboration tool
Team Name: Phoenix
| Monday | Tuesday | Wednesday | Thursday | Friday
Sanjay Bedudoori | 1) Started requirement document on "Task Management" module | 1) Completed documenting "Task management" module requirement | 1) | 1) | 1)
| 2) Complete pending part of requirement document for "tleask management" module | 2) Write test cases to the added requirements | 2) | 2) | 2)
| 3) No Obstacles | 3) Pending writing test cases to R1 and R2 | 3) | 3) | 3)
Venkata Bhardwaj Avasarala | 1)Prepared test cases for Google Drive integration. | 1)Completed functional specification of shared documents and Google drive integration | 1) | 1) | 1)
| 2)Prepare functional specifications document. | 2) Finish the functional specification document. | 2) | 2) | 2)
| 3)No major issues faced. | 3)No Major issues faced. | 3) | 3) | 3)
Sudharshan Reddy Kankara | 1) Worked on requirements document for use cases | 1) Worked on Test cases for chat application | 1) | 1) | 1)
| 2) Need to work on test cases for chat application | 2) Need to work on completion of requirements for chat application | 2) | 2) | 2)
| 3) No obstacles till now | 3) No obstacles till now | 3) | 3) | 3)
Shravani Alampalli | 1) Prepared test cases for task assigning | 1) Wrote the data management plan | 1) | 1) | 1)
| 2) Write the data management paln | 2) Finish the data management plan | 2) | 2) | 2)
| 3) No Issues | 3) No issues | 3) | 3) | 3)
Hemanth Sai Kishore Nersu | 1) Worked on mid term presentation | 1) completed working on requiremnets | 1) | 1) | 1)
| 2) should work on chat tool requirement | 2) Should work on issue tracking documnet | 2) | 2) | 2)
| 3) No issues | 3) No obstacles | 3) | 3) | 3)
Anudeep Reddy Mallidi | 1)Mid term presentation is finalised and contributed in writing test cases for shared calender requirement | 1)Finished test case documentation | 1) | 1) | 1)
| 2)Need to work on integrating,documenting test cases | 2)Need to work on finalising the documents for wednesdays submission and give them a final proof reading | 2) | 2) | 2)
| 3)No issues | 3)No issues | 3) | 3) | 3)
Vineeth Gajula | 1) Developed Test cases for Shared Calendar | 1) Finished the Project Management Plan for the project | 1) | 1) | 1)
| 2) Write the Project Management Plan | 2) Design Gantt Charts to show the amount of work done for this project | 2) | 2) | 2)
| 3) No Issues | 3) No issues | 3) | 3) | 3)
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?